## Sheet1
Week | Date | Task | Libraries to be used | Status
Week 1 | 21st Jan – 27th Jan | Pre-processing Data / Data Cleaning / Data Augmentation / Data Synthesis | Pandas, Numpy
Week 2 | 28th Jan – 3rd Feb | Implementing ML classification models: Logistic Regression, Naive Bayes, k-NN, SGD, Decision Tree, Random Forest, SVM, Ensembles - Hyperparameter Tuning | scikit-learn
Week 3 | 4th Feb – 10th Feb | Data Visualisation & Analysis & Model Validation & Testing | matplotlib, seaborn
Week 4 | 11th Feb – 17th Feb | Explore and start implementing Azure ML Services | Azure Free Trial Starts
Week 5 | 18th Feb – 24th Feb | Explore Data Storage | Azure Kubernetes
Week 6 | 25th Feb – 3rd Mar | Create Image, register with Docker
Week 7 | 4th Mar – 10th Mar | Develop Front End | Flask
Week 8 | 11th Mar – 17th Mar | Deploy as a web service (both within and outside of Azure)
Week 9 | 18th Mar – 24th Mar | API Testing and Validation
Week 10 | 25th Mar – 31st Mar | Scaling up of AKS and handling various loads
Week 11 | 1st Apr – 5th Apr | Report & Documentation